## Blad1
| week 38 | week 39 | week 40 | week 41 | week 42 | week 43 | week 44 | week 45 | week 46 | week 47 | week 48 | week 49 | week 50 | week 51
Database opstellen | bar: week 38
Layout website
Contact pagina | bar: week 39
Login / logout | bar: week 39 to week 40
Door producten kijken | bar: week 41 to week 42
Bestellen | bar: week 42 to week 44
KA overzicht bestellingen * | bar: week 44 to week 45
KA wachtwoord wijzigen * | bar: week 45 to week 46
KA adres gegevens wijzigen * | bar: week 46 to week 47
Categorie beheer | bar: week 41 to week 42
Merk beheer | bar: week 42 to week 43
Product beheer | bar: week 43 to week 44
Overzicht bestellingen | bar: week 44 to week 45
Afwerken / Optionele functies | bar: week 46 to week 50
Acceptatie test | bar: week 51
* KA = Klant Account
Algemeen = | bar: week 38
Gerrit de Groot = | bar: week 38
Timon de Groot = | bar: week 38